## Local Rec calendar summary
|  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2
| 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01
SF FSTF Calendar 2022-23
CCSF Budget Cycle | 2022-12-01: Departments Develop Proposed Budget; 2023-03-01: Mayor & Office of Public Policy & Finance Review; 2023-06-01: Board of Supervisors Review & Enactment of Budget; 2023-12-01: Departments Develop Proposed Budget; 2024-03-01: Mayor & Office of Public Policy & Finance Review; 2024-06-01: Board of Supervisors Review & Enactment of Budget
Budget Deadlines | 2022-10-01: Budget Instructions Issued; 2023-01-01: Department Submit Budget Requests; 2023-04-01: Mayor Submits Enterprise Dept Budget; 2023-05-01: Mayor Submits General Fund Dept & Capital Budgets; 2023-06-01: BOS Review + Add Backs; 2023-07-01: Budget Enacted; 2023-08-01: Mayor Signs Budget; 2023-12-01: Budget Instructions Issued; 2024-02-01: Department Submit Budget Requests; 2024-04-01: Mayor Submits Enterprise Department Budget; 2024-05-01: Mayor Submits General Fund Department & Capital Budgets; 2024-07-01: Budget Enacted; 2024-08-01: Mayor Signs Budget; 2024-12-01: Budget Instructions Issued | Budget Instructions Issued |  |  | Department Submit Budget Requests |  |  | Mayor Submits Enterprise Dept Budget | Mayor Submits General Fund Dept & Capital Budgets | BOS Review + Add Backs
| 2022-10-01: Q2; 2023-01-01: Q3; 2023-04-01: Q4; 2023-07-01: Q1; 2023-10-01: Q2; 2024-01-01: Q3; 2024-04-01: Q4; 2024-07-01: Q1; 2024-10-01: Q2 | Q2 |  |  | Q3 |  |  | Q4
| 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2023-10-25 | 2023-11-25 | 2023-12-25 | 2024-01-25 | 2024-02-25 | 2024-03-25 | 2024-04-01 | 2024-05-01 | 2024-06-01
FSTF Meetings
Agenda items related to 2022 Recommendations
FSTF Staffing: Full-time (FT) and .5 position | 2022-09-01: Post FSTF FTE position "Health Coordinator 2"; onboard .5 FTE staff; 2022-10-01: Continue onboarding .5 FTE staff; 2023-01-01: Interview & select FY candidate; onboard new FT staff; 2023-04-01: Complete
2024 Recommendations | 2022-10-01: 1) Update 2022 recommendations (approve Nov/Dec Meeting); Graphic design; 2023-01-01: Finalize recs; set up meetings; prep slide deck; disseminate recommendations; complete 80% of meetings; develop next steps from meetings; 2023-04-01: Follow-up meetings; implement identified next steps; 2023-10-01: Food Equity Report deadline | Begin pulling data for 2024 Recommendations, developing narrative and framework |  |  | Proposed hearing to present on 2024 Recommendations
Funding Equity - Special Revenue | 2022-09-01: Identify which groups oversee special revenue ( i.e. Prop C); 2023-01-01: Schedule meetings with groups oversee special revenue (i.e. Prop C) re: plans to address food/nutrition security
Budget Asks | 2022-09-01: Initial discussion about SF budget cycle; 2023-01-01: Determine FSTF budget ask guidelines/role; develop next steps | Utilize BFSR for development of budget asks
FSTF Configuration | 2022-10-01: New member recruitment; 2023-01-01: New member confirmation and on-boarding; 2023-07-01: New member nominations | FSTF elects new chair and vice-chair (October)
Ensuring Community Voice & Community Leadership | bar: 2022-09-01 to 2022-12-01; 2023-07-01 to 2024-12-01
ISSUE ACTION AREAS
Housing & Food | 2022-09-01: Recruit via email for sub-committees: reach out to Anne Quaintance see if she will lead this; 2023-01-01: 1) Conveen group to develop issue/info brief:; 2023-07-01: Check in with Anne re: what support is needed from FSTF
Medi-cal/CalAIM | 2022-09-01: Schedule meeting with SF Health Plans about adopting food interventions w/CA advancing & innovative Medi-Cal; 2022-10-01: Schedule & Meet with SF Health Plan;; 2023-01-01: Update in FSTF Mtgs; determine next steps; 2023-04-01: SF Health Plan to opt into full spectrum of MSF interventions by June 2023 | Presentation in November/December re: Health Plan
Centralized Food Body within Gov | 2023-07-01: 1) form steering group 2) create 2 pager summary 3) launch first subcommittee meeting | Continue hosting subcommittee meetings, establish roles, actionable goals of subcommittee |  |  | Develop recommendations to bring back to full task force to vote on, present final recommendations to city leaders
Food Equity Report | 2022-09-01: Schedule meeting with DPH (Ayanna Bennett?) on plan for Food Equity Report & how FSTF can support. Ask DPH for a timeline.; 2022-10-01: Schedule meeting with DPH (Ayanna Bennett) on plan for Food Equity Report & how FSTF can support. Ask DPH for a timeline.; 2023-01-01: 1) FSTF develops expectations for report and how FSTF is involved; 2) meet with DPH about Food Equity Report and info required; 3) develop timeline & next steps; 2023-04-01: Data gathering; 2023-07-01: Develop recommendations; Hold special meetings: 8/30 and 9/19 Input and review; Oct Deadline | Hold special meetings in October and November, new report deadline of December 1
Funding for Equity | 2023-01-01: Included in Recommendations 2023 - including equitable food supports | Utilize BFSER for development of equity-focused asks
Funding for Equity: Special | 2022-09-01: Recruit via email for sub-committees; 2022-10-01: Hold 1st meeting
Funding for Equity: General
Funding for Equity: Other
Food Recovery | 2022-10-01: Determine timeline; Schedule & Meet with SF Environment about SB 1383; 2023-04-01: Complete; 2023-07-01: SFE - Food Recovery Convening kick off
Community Food Policy Body | 2022-09-01: Meet with steering committee members to see how FSTF can support efforts/collaborate et al.; 2023-01-01: Meet with FAACTS and other groups to see how FSTF can support efforts/collaborate, etc.; 2023-04-01: Continue to meet with groups; 2023-07-01: Continue to meet with groups | See line 20
Meet with Gov Officials/Dept. Leads
HSH Director, Shireen Mcspadden | 2022-09-01: AQ initial conversation, will let FSTF know next steps; 2023-01-01: Schedule and conduct meetings | Schedule and meet with Directors after FSTF recommendations are ready |  |  | Schedule and meet with Directors and BOS after FSTF recommendations and BFSER are ready
HSA Director, Trent Rhorer
DPH Director, Grant Colfax
DAS Director, Kelly Dearman
BOS District 1: Connie Chan | 2023-01-01: Schedule and conduct meetings; determine next steps
BOS District 2: Catherine Stefani
BOS District 3: Aaron Peskin
BOS District 4: Joel Engardio
BOS District 5: Dean Preston
BOS District 6: Matt Dorsey
BOS District 7: Myrna Melgar
BOS District 8: Rafael Mandelman
BOS District 9: Hillary Ronen
BOS District 10: Shaman Walton
BOS District 11: Ahsha Safai
Emerging Issues
Rising Food Costs | bar: 2022-09-01 to 2022-12-01; 2023-07-01 to 2024-12-01
Disaster Food Planning | 2022-10-01: Reach out to DEM | Asked DEM or other city dept to present at FSTF on 9/22
HOTC Farmers Market - Food Access | 2023-07-01: Monitoring - FSTF sent letter urging no negative impacts to vendors/residents with relocation
More Info
Whole Household Coverage | [28 empty] | Reviewing responses from reporting agencies for BFSER | bar: 2022-10-01 to 2022-12-01; 2023-07-01 to 2023-09-01
Info & Referal - Outreach | [28 empty] | To be included in BFSER | bar: 2022-10-01 to 2022-12-01; 2023-07-01 to 2023-09-01
Info & Referal - Centralized | [28 empty] | To be included in BFSER | bar: 2022-10-01 to 2022-12-01; 2023-07-01 to 2023-09-01
Direct Cash Benefits | bar: 2022-10-01 to 2022-12-01; 2023-07-01 to 2023-09-01
Urban Agriculture | [28 empty] | To be included in BFSER, Parks and Rec. reporting agency provided data | bar: 2022-10-01 to 2022-12-01; 2023-07-01 to 2023-09-01
Transportation | [28 empty] | brief to be included in BFSER | bar: 2022-10-01 to 2022-12-01; 2023-07-01 to 2023-09-01